## Product Backlog
Planned Sprint | Actual Sprint | User ID | User Story Description | MoSCoW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | U1 | As a user, I want a login system so that only authorized users can access the dashboard | Must | None | You | Done
Sprint 1 | Sprint 1 | U2 | As a user, I want to input target IP/domain for scanning | Must | Login System | You | Done
Sprint 2 | Sprint 2 | U3 | As a user, I want the system to perform network scanning using Nmap | Must | Target Input | You | Done
Sprint 2 | Sprint 2 | U4 | As a user, I want parsed scan results in structured format | Must | Scanner Module | You | Done
Sprint 2 | Sprint 2 | U5 | As a user, I want VirusTotal integration for threat intelligence | Should | Internet/API Access | You | Done
Sprint 3 | Sprint 3 | U6 | As a user, I want risk scoring based on exposure and threat | Must | Scan Data | You | Done
Sprint 3 | Sprint 3 | U7 | As a user, I want severity classification (Low, Medium, High, Critical) | Must | Risk Engine | You | Done
Sprint 3 | Sprint 3 | U8 | As a user, I want dashboard visualization with charts | Should | Analysis Engine | You | Done
Sprint 4 | Sprint 4 | U9 | As a user, I want email alerts for high-risk vulnerabilities | Should | SMTP Setup | You | Done
Sprint 4 | Sprint 4 | U10 | As a user, I want PDF report generation for scan results | Could | Data Processing | You | Done
Sprint 4 | Sprint 4 | U11 | As a user, I want to download scan results as CSV | Could | Data Table | You | Done
Sprint 4 | Sprint 4 | U12 | As a user, I want geo-location mapping of IP addresses | Could | External API | You | Done
Sprint 4 | Sprint 4 | U13 | As a user, I want history of previous scans stored | Won’t | Database Setup | You | Done
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7